## project_timeline
Dissertation - Project Plan v/s Execution Timeline
Tasks | Start Date | Days | End Date
Exploring possible topics. | 2023-09-09 | 3 | 2023-09-12
Finalize topic with a supervisor. | 2023-09-12 | 6 | 2023-09-18
Research. | 2023-10-17 | 255 | 2024-06-27
Finalizing research and question. | 2023-11-20 | 20 | 2023-12-10
Research - Literature review. | 2024-01-10 | 40 | 2024-02-19
First simulation model with no UI. | 2024-01-19 | 18 | 2024-02-05
Early Prototype | 2024-02-05 | 11 | 2024-02-15
Evaluation, Research, Update | 2024-02-16 | 90 | 2024-05-15
Finalize mechanisms to model. | 2024-02-22 | 10 | 2024-03-03
Capture model in rules & diagrams. | 2024-03-04 | 10 | 2024-03-14
Make UI mock-up. | 2024-03-16 | 5 | 2024-03-21
Make low-fi prototype. | 2024-03-24 | 10 | 2024-04-03
Test low-fi prototype. | 2024-05-01 | 5 | 2024-05-06
Improve. | 2024-05-08 | 10 | 2024-05-18
Focused Development. | 2024-05-16 | 34 | 2024-06-18
Develop MVP (high-fi prototype). | 2024-05-20 | 20 | 2024-06-09
Test hi-fi prototype. | 2024-06-12 | 10 | 2024-06-22
Bridge To College Learning Session. | 2024-06-19 | 1 | 2024-06-19
Refine based on feedback. | 2024-06-20 | 8 | 2024-06-27
Refine application. | 2024-06-24 | 30 | 2024-07-24
Write final report - draft 1. | 2024-06-28 | 35 | 2024-08-01
Refine Report & Submit. | 2024-08-03 | 10 | 2024-08-12
Field experiment. | 2024-07-25 | 5 | 2024-07-30
Finish/Refine Written Thesis. | 2024-08-01 | 18 | 2024-08-19
Write Dissertation | 2024-02-22 | 179 | 2024-08-19
COLOUR LEGEND
|  | = | Actual
|  | = | Plan
|  | = | Evaluation
|  | = | Dropped
Formulas:
End Date = [Start Date]+[Days]

## gantt_chart
Dissertation - Project Plan
Tasks | Start Date | Days | End Date
Exploring possible topics. | 2023-09-09 | 3 | 2023-09-12
Finalize topic with a supervisor. | 2023-09-12 | 6 | 2023-09-18
Finalizing research and question. | 2023-11-20 | 20 | 2023-12-10
Research - Literature review. | 2024-01-10 | 40 | 2024-02-19
Finalize mechanisms to model. | 2024-02-22 | 10 | 2024-03-03
Capture model in rules & diagrams. | 2024-03-04 | 10 | 2024-03-14
Make UI mock-up. | 2024-03-16 | 5 | 2024-03-21
Make low-fi prototype. | 2024-03-24 | 10 | 2024-04-03
Test low-fi prototype. | 2024-05-01 | 5 | 2024-05-06
Improve. | 2024-05-08 | 10 | 2024-05-18
Develop MVP (high-fi prototype). | 2024-05-20 | 20 | 2024-06-09
Test hi-fi prototype. | 2024-06-12 | 10 | 2024-06-22
Refine application. | 2024-06-24 | 30 | 2024-07-24
Field experiment. | 2024-07-25 | 5 | 2024-07-30
Finish/Refine Written Thesis. | 2024-08-01 | 18 | 2024-08-19
Write Dissertation | 2024-02-22 | 179 | 2024-08-19
Formulas:
End Date = [Start Date]+[Days]

## tool_critique
INFORMATIVE TOOL → QUALITY ↓ | FOSTER FOREST | MINE SET | ABOUT THAT FOREST | FOREST KIDS | SIMFOREST | MYCROFOREST
REALISTIC | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
ENGAGING | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
EASILY ACCESSIBLE | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
FOR YOUTH | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
TEAM | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
SOLO | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
FOCUSED AIM | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
FOREST MANAGEMENT | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
FOREST AS CARBON SINK | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
FINANCIAL MOTIVE | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
LOW ENTRY THRESHOLD | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
EASY TO USE UI | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫
SUFFICIENT BUILT IN HELP | ⚫ | ⚫ | ⚫ | ⚫ | ⚫ | ⚫

## avoiding_bad_design
PROBLEM |  | COUNTER MEASURES TAKEN
RIGIDITY | Difficult to change. | Separation of concerns by sticking to the Model View Controller design pattern. Underlying model is separate from React components and is organized into classes in an Object Oriented Fashion.
FRAGILITY | Prone to breaking. | Modular testing (app and specific components tested immediately after implementation of each new feature). GitHub for version control. Lessen rigidity.
IMMOBILITY | Difficult to reuse. | Choice to use ReactJS allows for creation of reusable components. Example: <Button/>, <Switch/>, <Card/>, <Veil/>, etc.
VISCOSITY | Hacks over the right thing. | Temporary fixes were avoided or immediately replaced as soon as correct solution was identified. Example: Decision to change structure of code early on and start afresh instead of continuing work on initial prototype code.

## MVC
Model | View | Controller
Handles data. | Displays data to users. | Bridge between Model and View.
Handles bussiness logic. |  | Handles user input.
Processes data. | Passes user input to controller. | Updates model.
Responds to information requests. |  | Ensures view reflects changes.

## env_vars
Tree |  | Carbon Dynamics
BIODIVERSITY_STRESS_REDUCTION_FACTOR C_PC_TREE C_WEIGHT_SCALE_FACTOR DECAY_HEIGHT_THRESHOLD HEIGHT_MAX HEIGHT_START_SEEDLING LIFE_STAGE_TREE REPRODUCTION_INTERVAL REPRODUCTION_STRESS_THRESHOLD TOLERANCE_CO2 TREE_REMAINS_AFTER_FELL STRESS_AGING STRESS_RECOVERY_FACTOR WOOD_DENSITY WOOD_DRY_WEIGHT_PC |  | C_START C_PC_DECAY CO2_FOSSIL_FUEL_ANNUAL_EMISSION_START TREE_VOLUME_MAINTENANCE_PC DECAY_PC_SOIL SOIL_RELEASE_PC
Land
BIODIVERSITY_CATEGORIES LAND_AGE_COMP LAND_FREE_PC_START LAND_SIZE SPECIES_COMPOSITION_START
Finances | Time | Targets
COST_MGMT_ACTION FUNDS_START INCOME_SOURCES | INIT_NUM_YEARS TIME_MAX SIMULATION_DELAY | TARGET_CO2_START TARGET_INCOME_START
Forest Management |  | Air
ROTATION_START TIMBER_USAGE |  | AIR_MASS ENV_SCALE ENV_SCALE_COLORS

## ui_components
Norman's Model | Task-Core Language Mapping | Jacob Nielsen's Usability Heuristics
(i) Goal establishment. | (i) Articulation: User maps their goals to actions. | (i) Use simple language with no irrelevant information.
(ii) Intention formation. |  | (ii) Speak the user's language.
(iii) Action sequence specification. | (ii) Performance: System interprets user actions correctly and responds appropriately. | (iii) Minimize memory load.
(iv) Maintain consistency.
(iv) Action execution. |  | (v) Provide timely and apt feedback.
(v) System state perception. | (iii) Presentation: System presents updated state. | (vi) Clearly mark exits.
(vi) System state interpretation. |  | (vii) Incorporate shortcuts for expert users.
| (iv) Observation: Users update mental model based on presented changes. | (viii) Display good error messages.
(vii) System state evaluation. |  | (ix) Design to prevent errors.
(x) Ensure help is readily available.

## data
Data: | Years | Tree Type | Tree Age | Tree Position | Income
Description: | Current year in simulation. | Coniferous or deciduous. | Age of the tree. | Position [x, y] of tree on land grid. | Money earned.
Type: | Quantitative Discrete | Categorical Nominal | Quantitative Discrete | Categorical Nominal | Quantitative Continuous
Data: | Expenses | Biodiversity | Total Money | CO2 | Carbon
Description: | Money spent. | How biodiverse is the land? | Bank balance. | Atmospheric CO2 concentration. | Amount of carbon in various reservoirs.
Type: | Quantitative Continuous | Quantitative Continuous | Quantitative Continuous | Quantitative Continuous | Quantitative Continuous
Data: | Action Type | Action Tree Affected | Action Year | Action Num Trees Affected | Is Action Successful
Description: | Fell or plant. | Type and age of the tree targeted by the action. | Year at which the action is to be executed. | The no. of trees that the action is to affect. | Successful, partially successful, failure.
Type: | Categorical Nominal | Categorical Nominal | Quantitative Continuous | Quantitative Discrete | Categorical Ordinal
Data: | Is Action Repeated | Target Values | Is Target Met | Is Income Stream Active | Is Serious Mode
Description: | Whether this action is to be repeated periodically. | Set CO2 or income target. | Whether target is met. | Whether an income stream is active. | Whether to display if targets are met or not.
Type: | Categorical Binary | Quantitative Continuous | Categorical Binary | Categorical Binary | Categorical Binary

## sim mw games key ideas
Simulation | Graphical feedback accompanied by short, embedded multimedia explanations result in better understanding of ideas by students compared to when only graphical or textual feedback was provided instead. | Most students learn from microworlds only when exploration occurs within context of some carefully designed learning activity that provides structure. | Microworld
Providing short explanations intermittently boosts understanding as this makes it easier for learners to link thoughts to experiences. The alternative of a tutorial is less effective because it separates explanation from experience.
| Learners consistently reported lesser frustration when feedback was graphical rather than textual. | Students who engaged in content related discussions demonstrated increased learning. | Game
| Instructional support is best provided while students use the simulation as opposed to before, because the latter can lead to students forming early hypotheses that are generally hard to displace later even if evidence points against it. | Three game characteristics most favored by children in a study wherein student designed games were evaluated by other students were (i) storyline quality, (ii) competition, and (iii) appropriate challenge.
Students significantly benefit from simulations that build up complexity in stages allowing enough time for developing a good grasp on easier tool mechanics and ideas before moving on to more complex ones. That is, model progression is beneficial.

## pedagogy best practices
Piagetian Learning Theory | Good Practices
(i) Epistemic conflict. | (i) Structure learning activities around challenges to introduce gamification.
(ii) Self-reflection. | (ii) Having multiple challenges at varying levels of difficulty increases the likelihood of learners finding a challenge optimal.
(iii) Self-regulation. | (iii) Model progression is beneficial.
Flow Theory | (iv) Good UX is key to avoiding learner frustration.
(i) Optimized challenge level. | (v) Graphical feedback accompanied by short, embedded multimedia explanations boosts understanding and reduces frustration.
(ii) Holds attention.
(iii) Clear goals. | (vi) Guidance during interaction with the tool improves learning.
(iv) Clear feedback. | (vii) Ensure students explore the microworld within the context of a structured activity to ensure learning.
(v) Absorbing experience.
(vi) Sense of control. | (viii) Topic related discussions boost understanding.
(vii) Frees learner of self-consciousness. | (ix) Students find a storyline, an important motivator and construct using which to mentally relate to the tool.
(viii) Hastened sense of time.

## challenges
| Goal | Active Features | Possible Learnings | Expected Learner Activity
Challenge 1 | Maximize income from the forest. | Timeline Land Money Viewer Plan Viewer Planner Timber Income Stream | # Timber is profitable resource. This motivates deforestation. # Generally, forest management activities are performed in rounds. | # Create management plans that chop as many trees as possible. # Note down income. # Edit plan. Try changing rotation period. # Coniferous trees are more profitable. Try planting only coniferous trees.
Challenge 2 | Keep atmospheric CO2 concentration at as desirable a value as possible. | Challenge 1 Features + CO2 Target Setter + CO2 Scale - Money Viewer | # Forests are crucial to keeping CO2 levels in check as they sequester CO2. # Mature and older trees are needed to keep atmospheric CO2 levels low. # Mature trees absorb more carbon as they grow. But older trees store more CO2. # Chopping an older tree releases more CO2 at once than chopping a mature tree. # Clear felling is the worst strategy. # Thinning is a better idea. # No management is the best strategy. | # Activate CO2 target. # Try best plan from challenge 1. Note highest CO2 concentration figure across 300 years. # Set a slightly lower concentration value as target. # Tweak management plan. # Try to hit lower CO2 target. # Repeat last 3 steps.
Challenge 3 | Maximize income while trying to keep CO2 concentration ideal. | Challenge 2 Features + Money Viewer | # It is impossible to keep CO2 levels in a safe range without lowering profit margins. | # Set both CO2 target and income target. # Tweak plan and see if targets are achieved. # Report lowest CO2 + highest Income target combination achieved.
Challenge 4 | How long before fossil fuel usage leads to critical CO2 levels (red) or complete forest death in the microworld? How to increase this time? | Challenge 3 Features + Fossil Fuel Usage Panel + Carbon Distribution Panel + Biodiversity Score & Land Class | # Only way to improve CO2 concentration in the air is to significantly cut down fossil fuel emissions. No silver bullet. # There is more carbon trapped within earth as fossil fuels than there is in the air and vegetation. | # Set fossil fuel usage emission to current global level of 10 GtC and observe how many years pass before CO2 levels reach critical levels and the entire forest dies out. # Tweak plans to see if some management strategy can keep carbon levels in check. # Realize that this is not possible. Only way to reduce atmospheric CO2 concentration is to reduce emissions.
Challenge 5 | How helpful is diversifying income from forests? | Challenge 4 Features + NTFP Income Stream + Recreation Income Stream | # Other income streams are not very profitable. Neither are they as reliable as timber. # There is a need to research more ways of earning from a forest that does not involve chopping down trees. # Means of earning from forests such as forest recreation that involves building infrastructure requires large upfront investment. | # Activate other income streams. # Compare per year, per rotation, and overall income and expenses of these other streams with that of the default timber stream.

## challenges_bridge2college
Challenge | Goal | Active Features
1 | Maximize income from the forest. | Timeline, Land, Money Viewer, Plan Viewer, Planner, Timber Income Stream
2 | Keep atmospheric CO2 concentration at as desirable a value as possible. | Challenge 1 Features + CO2 Target Setter + CO2 Scale - Money Viewer

## tool_pros_cons
Foster Forest
Pros | Cons
Tool is very flexible and supports a rich variety of scenarios. Participants can come up with creative strategies not severely limited by tool capabilities. | Participants must be familiar with the domain. Not for the lay man.
Participants found the UI too mathematical and hard to relate to.
Participants cannot interact with the tool directly. They must rely on the facilitator.
Tool is realistic with well a designed ABM. | Tool requires extensive introductory training and user guides.
Participants appreciated being able to test strategies in a risk-free environment. | Tool use instructional material (2 usage videos, 6 booklets one for each role + facilitator) provided was overwhelming for some participants. Thus, learning curve is very high.
Participants enjoyed the ComMod wherein decisions followed group discussions. | This tool requires an elaborate set up with 2 projectors and a facilitator. It was built using software that needs to be downloaded and installed along with associated user guide materials. This makes this tool less accessible.
Mine Set
|  | Pros | Cons
|  | ComMod. | Allegorical model is less scientifically accurate.
Engaging and immersive.
|  | Models a rich variety of land use change drivers. | Significant set up required.
|  | Incorporates model progression to gradually reveal game complexity. | No explicit mention of climate change.
|  | Caters to a wide audience, particularly forest stakeholders. However, non-expert audiences can also enjoy and learn from it. | The physical nature of the game requires in-person attendance. This makes it less widely accessible unless online collaborative tools (like zoom, google meet, etc.) are incorporated and a third party coordinates and communicates all player moves. This is tedious.
The physical mine set board game is a more holistic visceral experince that is more likely to be remembered given close in-person interaction with peers and physical interaction with game pieces.
About That Forest
|  |  |  | Pros | Cons
|  |  |  | Underlying code allows for easily modifiable settings. | Underlying model and research not openly available.
ComMod.
Engaging.
Competition in addition to cooperation.
|  |  |  | Multiple economic drivers of exploitation. | Atmospheric CO2 levels is not a modelled indcator.
Widely accessible.
Appeals to a wide age group and range of starting knowledge levels.
Forest Kids
[6 empty] | Pros | Cons
[6 empty] | Age appropriate for children. | No learning through making.
[6 empty] | Visually very attractive. | Facts presented during matching and memory games are random and lack connection. This can make them hard to learn.
Great user experience with smooth interactions.
[6 empty] | Motivating mini-games. | Games are very engaging. The timing element adds a sense of urgency. As pointed out by [], games that are very competative or engaging, often with a scoring mechanism, especially in the absence of constructionist mechanisms, can significantly effect learning negatively. Users tend to enter a "twitch" mode where they are hyperfocused on improving score and learning suffers. This is a real threat in this game. Personally, when trying the memory game, I soon found myself ignoring the facts as I focused more on memorizing tile symbols to get the matches right before the timer runs out to score maximum points.
Very informative and covers different topics related to forest biodiversity and Earth's climate.
In-app help is well placed and provided in small, easy to absorb chunks.
Text in the game is supported by audio readouts to make it easier to absorb for children.
Facts are repeated from time to time but not too frequently. This may promote information persistence in memory.
SimForest
[8 empty] | Pros | Cons
[8 empty] | Rich set of manipulatable controls. | Does not consider atmospheric CO2 levels.
General forest growth simulation around which multiple learning scenarios may be developed.
Can be adapted to teach a range of age groups and expertise levels (school grade 4 all the way up to university graduate students and forestry professionals).
[8 empty] | Facilitates inquiry-based constructivist learning comprising multiple iterative inquiry cycles with steps (i) ask question or form hypothesis, (ii) plan to answer or test hypothesis (iii) note observations, (iv) analyze data gathered, (v) communicate learnings. | Only available on PC and requires download and possibly some set up (OS, Java, or Swing related compatibility issues possible).
Clean user-friendly UI.
[8 empty] | Allows moving through times at various speeds. | Does not consider economic value of forests.
Good data visualization.
Allows multi-level control (high-level or black box, as well as low-level or glass box).