## project_timeline
Dissertation - Project Plan v/s Execution Timeline
Tasks | Start Date | Days | End Date
Exploring possible topics. | 2023-09-09 | 3 | 2023-09-12
Finalize topic with a supervisor. | 2023-09-12 | 6 | 2023-09-18
Research. | 2023-10-17 | 255 | 2024-06-27
Finalizing research and question. | 2023-11-20 | 20 | 2023-12-10
Research - Literature review. | 2024-01-10 | 40 | 2024-02-19
First simulation model with no UI. | 2024-01-19 | 18 | 2024-02-05
Early Prototype | 2024-02-05 | 11 | 2024-02-15
Evaluation, Research, Update | 2024-02-16 | 90 | 2024-05-15
Finalize mechanisms to model. | 2024-02-22 | 10 | 2024-03-03
Capture model in rules & diagrams. | 2024-03-04 | 10 | 2024-03-14
Make UI mock-up. | 2024-03-16 | 5 | 2024-03-21
Make low-fi prototype. | 2024-03-24 | 10 | 2024-04-03
Test low-fi prototype. | 2024-05-01 | 5 | 2024-05-06
Improve. | 2024-05-08 | 10 | 2024-05-18
Focused Development. | 2024-05-16 | 34 | 2024-06-18
Develop MVP (high-fi prototype). | 2024-05-20 | 20 | 2024-06-09
Test hi-fi prototype. | 2024-06-12 | 10 | 2024-06-22
Bridge To College Learning Session. | 2024-06-19 | 1 | 2024-06-19
Refine based on feedback. | 2024-06-20 | 8 | 2024-06-27
Refine application. | 2024-06-24 | 30 | 2024-07-24
Write final report - draft 1. | 2024-06-28 | 35 | 2024-08-01
Refine Report & Submit. | 2024-08-03 | 10 | 2024-08-12
Field experiment. | 2024-07-25 | 5 | 2024-07-30
Finish/Refine Written Thesis. | 2024-08-01 | 18 | 2024-08-19
Write Dissertation | 2024-02-22 | 179 | 2024-08-19
COLOUR LEGEND
|  | = | Actual
|  | = | Plan
|  | = | Evaluation
|  | = | Dropped
Formulas:
End Date = [Start Date]+[Days]