## My Schedule
From | To | # Days | Activity | Today | # Days Left | Achieved?
2024-05-15 | 2024-06-09 | 25 | Development | 2024-07-13 | 0 | Almost
2024-06-09 | 2024-06-19 | 10 | Evaluation | 2024-07-13 | 0 | Yes
2024-06-19 | 2024-06-27 | 8 | Refinement | 2024-07-13 | 0 | Yes
2024-06-27 | 2024-08-01 | 35 | Writing | 2024-07-13 | 19 | Yes
Formulas:
To = [From]+C2
From = [To, row above]

## Product Backlog
Task | Effort | Importance | Status
Update biodiversity score to promote mixed ages. | 3 | 3 | To Do
Plant action selector restriction. | 3 | 1 | To Do
Update help. | 3 | 3 | In Progress
Add button response. | 3 | 1 | To Do
Stabilize Model | 3 | 3 | Done
Add evidence for tree documentation. | 3 | 3 | Done
Change Income Dependency to ON/OFF. | 3 | 3 | Done
Update income dependency bar to change with money made. | 3 | 3 | Done
Allow any year. Display rotations in planner. | 3 | 3 | Done
Show tree type on hover. | 3 | 3 | Done
Deployment | 3 | 3 | Done
Remove Target Income | 3 | 3 | Done
Tree info on hover. | 3 | 3 | Done
Step Buttons | 3 | 3 | Done
Income (overall, rotation, year) | 3 | 3 | Done
Expenses (overall, rotation, year) | 3 | 3 | Done
Set rotation income border such that it stays red throughout (forward in time) after a rotation has failed. | 3 | 3 | Done
Rotation Target Alert. | 3 | 3 | Done
Plot Simulation Data | 3 | 3 | Done
Walkthrough page. | 3 | 3 | Done
Show/Hide Components | 3 | 3 | Done
Handle situation when not enough money. | 3 | 3 | Done
Landing page. | 3 | 3 | Done
Per rotation income target. | 3 | 3 | Done
Fix bug = + income even with 0 dependency. | 3 | 3 | Done
Maintenance and fixed cost of alternate income streams. | 3 | 3 | Done
Partially Executed (Amber) Actions | 3 | 3 | Done
Base income and expendition from/on other streams on income dependency settings? | 3 | 3 | Done
Action add repeat bug. | 2 | 3 | Done
Prevent negative carbon emissions. | 2 | 3 | Done
Questionnaire | 2 | 3 | Done
User guide video. | 2 | 3 | Done
User guide presentation. | 2 | 3 | Done
Starting World | 2 | 3 | Done
5 mins presentation | 2 | 3 | Done
Update Challenges | 2 | 3 | Done
Change currency to coin. | 2 | 3 | Done
Challenge SetUp | 2 | 3 | Done
Bug - Pause when clicking on PLAN. | 2 | 3 | Done
Double Click Clear all | 2 | 3 | Done
Money unit change read. | 2 | 3 | Done
Targets - Invalid input bug. | 1 | 3 | Done
Change color | 1 | 3 | Done
Update intro. | 1 | 3 | Done
Fix Rotation Display & Save Load Bug | 1 | 3 | Done
Add "tree" to document model network. | 3 | 2 | Done
Add "plan" to document model network. | 3 | 2 | Done
Try to make recreation profitable. | 3 | 2 | Done
Allow 0 Rotation Planning | 3 | 2 | Done
Selective money break down. | 3 | 2 | Done
Help as "info" buttons instead of help page. | 3 | 2 | Done
Option to show/hide certain elements. | 3 | 2 | Done
Fossil fuel emissions. | 3 | 2 | Done
New growth while decaying. | 3 | 2 | Done
Cost of chopping depends on size of the tree. | 2 | 2 | Done
Range in CO2 scale on hover. | 1 | 2 | Done
Remove duplicate Funds instance. | 3 | 1 | Done
Buying & Selling Cost | 3 | 1 | Done
Disable key press until intro is complete once started. | 2 | 1 | Done
Line graphs to capture tree stress. | 2 | 1 | Done
Removes last year from plan in planner. | 2 | 1 | Done
Rotation Income Viwer Resource on hover. | 3 | 3 | Abandoned
Carbon release from lumber. | 3 | 3 | Abandoned
Make non-timber income streams based on profit numbers. | 3 | 3 | Abandoned
Try to Fix Biodiversity Score | 1 | 2 | Abandoned
Money unit change write. | 3 | 1 | Abandoned
Update CO2 scale. | 3 | 1 | Abandoned
Cost of living. | 3 | 1 | Abandoned
Loading page. | 3 | 1 | Abandoned
Page transitions | 3 | 1 | Abandoned
Alter maintenance carbon mechanism. | 3 | 1 | Abandoned
Help page visited leaf. | 2 | 1 | Abandoned
Add commas to numbers. | 2 | 1 | Abandoned
Reset on Home from Planner. | 2 | 1 | Abandoned
Respawn in same spot from parent. | 3 | 1 | Abandoned