## My Schedule
From | To | # Days | Activity | Today | # Days Left | Achieved?
2024-05-15 | 2024-06-09 | 25 | Development | 2024-06-12 | 0 | Almost
2024-06-09 | 2024-06-19 | 10 | Evaluation | 2024-06-12 | 7
2024-06-19 | 2024-06-30 | 11 | Refinement | 2024-06-12 | 18
2024-06-30 | 2024-08-01 | 32 | Writing | 2024-06-12 | 50
Formulas:
To = [From]+C2
From = [To, row above]

## TO DO
Task | Importance | Effort | Status
Model Improvement | 3 | 3 | To Do
Rotation Target Fail/Pass Bugs | 3 | 3 | To Do
Page transitions | 2 | 3 | To Do
Help done checker. | 2 | 3 | To Do
If target is not met, pause the world & display message. | 2 | 3 | To Do
Money unit change write. | 2 | 3 | To Do
Add commas to numbers. | 2 | 2 | To Do
Update CO2 scale. | 2 | 1 | To Do
Reset on Home. | 2 | 2 | To Do
Cost of living. | 2 | 3 | To Do
Option to show/hide certain elements. | 2 | 3 | To Do
Range in CO2 scale on hover. | 2 | 2 | To Do
Alter maintenance carbon mechanism. | 1 | 3 | To Do
Do not display decimal points. | 1 | 3 | To Do
Add button response. | 1 | 3 | To Do
Line graphs to capture tree stress. | 1 | 2 | To Do
Respawn in same spot from parent. | 1 | 2 | To Do
Removes last year from plan in planner. | 1 | 2 | To Do
Plant action selector restriction. | 1 | 3 | To Do
Walkthrough page. | 3 | 3 | Done
Show/Hide Components | 3 | 3 | Done
Challenge SetUp | 3 | 2 | Done
Bug - Pause when clicking on PLAN. | 3 | 2 | Done
Handle situation when not enough money. | 3 | 3 | Done
Landing page. | 3 | 3 | Done
Double Click Clear all | 3 | 2 | Done
Per rotation income target. | 3 | 3 | Done
Fix bug = + income even with 0 dependency. | 3 | 3 | Done
Maintenance and fixed cost of alternate income streams. | 3 | 3 | Done
Partially Executed (Amber) Actions | 3 | 3 | Done
Base income and expendition from/on other streams on income dependency settings? | 3 | 3 | Done
Action add repeat bug. | 3 | 3 | Done
Money unit change read. | 3 | 2 | Done
Targets - Invalid input bug. | 3 | 2 | Done
Fix Rotation Display & Save Load Bug | 3 | 1 | Done
Allow 0 Rotation Planning | 3 | 1 | Done
Fossil fuel emissions. | 2 | 3 | Done
New growth while decaying. | 2 | 3 | Done
Remove duplicate Funds instance. | 2 | 1 | Done
Cost of chopping depends on size of the tree. | 2 | 3 | Done
Rotation Income Viwer Resource on hover. | 1 | 2 | Done
Plot Simulation Data | 3 | 3 | In Progress